OUTCOMES DOCUMENT

Lower Chippewa Invasives Partnership Monthly Meeting

Community Services Building, Room 55, 3001 US HWY 12 East, Menomonie, WI 54751

Thursday, June 23, 2016, 2 - 4:30 PM

Present:  Chris Gaetzke, Mame Gale, Martin Van, Melanie Yager, Kathy Stahl, Jim Anderson, Ted Ludwig, Lisa Ludwig, Tim Jackson (Natural Resources intern)

LCIP Identity Statement:  LCIP is an organization that reaches goals toward invasive species awareness and control by using Civic Governance as a new approach to educate and organize the civic infrastructure needed to produce a basis to govern for the common good and sustain democracy as a just system.

Meeting Purpose:  To develop projects and organization that will meet 2016 goals and direction through the use of the Civic Governance approach.

- Approval of Outcomes Documents – May 26th, 2016. Chris changed contact name for Dunn F&G from Jim Anderson to Jim Thompson.  Motion by Kathy, second by Lisa to approve Outcomes Document as amended. Passed.

- Negotiate agenda and individual check-in (5 mins each)– identify progress in organizing key stakeholders in your jurisdictions and agreed individual action items

Tim described his first weeks of working. They drove the roads mapping the wild chervil to document where it is in northern and eastern Dunn County.

Jim reported that the county board passed the pollinator resolution at the last Dunn County board meeting. He suggested we could consider proposing a resolution regarding invasives. Gary Seipel, board member from Eau Galle, stated at the meeting there is a massive problem with wild parsnip in the western part of the county. Other supervisors mentioned not having sprayers to control invasives. Kathy brought up that 4 Control has a sprayer that can be rented at a reduced rate if the go through LCIP. This would avoid using a farm sprayer which requires considerable cleanup.

Ted had no new info on the fall Menomonie high school event. During phosphorus sample collection he drives past the sites where poison hemlock has been reported (220th St. north of Hwy 64) and there are several sites that had been sprayed in the fall. The leaves on the new growth look more like knotweed than hemlock so will check again in the near future and will verify sites with the person who reported it.

Lisa reported that a friend stated there was wild chervil on Hwy B west of Hwy 40. This should have been sprayed but it takes about 4 weeks for results to show.

Mame mentioned while on the road with Tim they talked to a resident and the subject was brought up how to find info on invasives. We talked about methods of reaching those who don’t get local papers. The list-serves and small papers like the Prairie Farm Review are possibilities.

Chris reviewed the focus questions from the annual meeting. Communication and coordination was a primary concern. Regional mapping is necessary and being worked on. A Google calendar is in the works. Google drive accounts have been started to help relay information. Project signage will help publicize our efforts.  Chris has contacted Jim Thompson of Dunn F&G about the garlic mustard coming up at their site. Chris told him what needed to be done and told him we could help if they needed it. He has not requested that.  He contacted Dunn County Fair and there would be a booth cost of $150.

- Address Governing Issues

Amur Cork tree action plan and grants

Chris showed photos of Phelan Park and the cork trees that had been cut. Stumps on neighboring property that hadn’t been treated are sprouting and those that had been girdled and treated were growing well. Japanese Barberry is showing up in the cleared area.  John Sippl did some research and found there will be some funding through EQIP for landowners with 5+ acres for control. There are some landowners in Eau Galle that would qualify. The DNR money for herbicide for cork could be used for control rural and non-rural areas. Kathy stated DNR will cover eradication only and not replacement trees. DNR has a separate fund for restoration. We need to map and estimate costs to get the funds. Work Group for mapping will be: Kathy, Mame, Martin, Melanie, Chris, and Tim. The DNR told Chris there are cork sites in Section 15, Dunn township near 420th Street. They haven’t noted any other sites in the area.

LCIP apparel

Melanie reported that vests are available for $18 + $3 for logo.  First round of shirts were ordered and received by LCIP members.

Invasive Crusader Award Winner Ceremony

Mame and Chris went to Horicon to accept the award for LCIP on June 9th. Award is engraved on buckthorn wood and displayed at the invasive education wall outside of Dunn Co LWCD office on third floor of the DC Government Center, 800 Wilson Ave.

Wild Chervil mapping and spraying update

The wild chervil project has stopped for the year as flowering is over. Kathy talked with Mark Renz and he doesn’t know when chervil seeds become viable.  Tim has gone out with several people mapping wild chervil throughout Dunn County working from the northeast to the west. Mame and her sister mapped some roads above Hwy. 64. Chervil is being found in all sun or shade conditions and all types of soils. Spraying was done by Lee in many areas including the town of Colfax and the site on Hwy. 25. Single plants that were mapped were treated. Lee has been paid for work done in Chippewa County. Dunn County has to be billed. The town of Howard and Chippewa County sprayed with 2-4-D, which is not effective on wild chervil. The multiple presentations to them emphasized using Escort but they didn’t want to use it in their sprayers. Probable reasons are Escort is a broadleaf and they had 2-4-D on hand. A news story video was made on wild chervil and wild parsnip with Kathy and Chris and it broadcast on the ABC(WQOW) channel and on their website. We can purchase the video for $25. Consensus was we could make good use of a copy of the video. The station will come back later to do a video on Amur Cork Tree in August/September.

2016 Natural Resources Intern

Tim has been working on wild chervil and will be involved in the Amur Cork Tree mapping. Other things will be working with the DNR foresters, wildlife crews, and fisheries crews (doing shocking). Other things are USFWS intern swap, NRCS projects and working with RCBMG on lake and stream monitoring.

Upcoming LCIP projects volunteer commitments and planning

The trailer shelving and hangers has been finished. Chris showed photos (also on LCIP Facebook page) of the completed project. Very little will be stored on the floor so it will be easy to clean. One of Mame’s amur cork tree slabs is hung on the wall.

Chris and Jim talked about the invasive tour on June 16th.  12 of the 18 seats on the bus were filled and many invasives were sighted. It continues to be a success.

Stockholm Art Fair will be manned by Kathy and Martin. Kathy will contact Pat about getting the display tent. Tables are available through Land Conservation. The lack of a banner was discussed.

Two presentations will be given at the Upper Midwest Invasives Species Conference in La Crosse on October 17-19th. About 600 people will attend. Kathy has attended and recommends attendance. Lee will have an exhibit there. Chris and Kathy will be presenting. Volunteers can get a reduced or free registration. See more information by going to this website.

Report financials and grant requests

Kathy reported savings balance was $1,000.05 and checking $907.51. Save the Hills grant of $1,500.00 included in this amount. Outstanding bill of $156.14 to Kathy for printing of the newsletters resulting in a balance of $1,343.86 for dedicated items and $412.50 not dedicated. We did not get the UW Center for Cooperatives grant and Kathy talked to the woman that handles these grants. Next year they will be more clear in the requirements for this grant.

Media articles and newsletter

Kathy had 200 copies of the newsletter printed. She feels that not all issues of the future newsletters need to be hard copies. Newsletters have been placed in the Menomonie Library and will be placed in medical offices by Chris, Tim and Kathy. Lisa said any library can distribute to the others using their courier system.  Newsletters will be published as needed. Jim said he would be willing to provide each County Board member with a copy.

Next newspaper article will be on Black Locust for July and then Purple Loosestrife as it will be blossoming in August written by Kathy.

Software

Kathy will contact Tony Summers about the software and the next steps we need to take to train and use it.

- Identify Next Steps

Next meeting is on Thursday, July 28th from 2-4:30 PM, Community Services Building Room 55, 3001 US HWY 12 East, Menomonie, WI 54751

- Evaluate the Meeting

June 2016 meeting score average was 4.99. Scores were 6x5.0, 4.99, and 4.90. Mame had to leave the meeting early.

Meeting adjourned at 4:29 P.M.